## Gantt Chart
Hospital Appointment Booking System |  | Project Start: Sun, Aug 2, 2026 Display Week: 01 |  |  |  | 2026-08-02 | [6 empty] | 2026-08-09 | [6 empty] | 2026-08-16
[6 empty] | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20
Company Name: NPB Hospital
Task | Assigned to | Progress |  | Start | End | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Phase 01: Setup & Requirements
Repository setup and collaborators | Bibhay Aryal |  | 100% | 2026-08-02 | 2026-08-03 | bar: S to M
README and repository structure | Bibhay Aryal |  | 100% | 2026-08-02 | 2026-08-03 | bar: S to M
Requirement gathering and evidence | Bibhay Aryal |  | 100% | 2026-08-02 | 2026-08-05 | bar: S to W
Project scope and stakeholder analysis | Bibhay Aryal |  | 100% | 2026-08-03 | 2026-08-04 | bar: M to T
Functional and non-functional requirements | Bibhay Aryal |  | 100% | 2026-08-04 | 2026-08-06 | bar: T to T
Product backlog and user stories | Priyanka + Neharika |  | 100% | 2026-08-02 | 2026-08-05 | bar: S to W
Trello board and Sprint 1 planning | Priyanka + Neharika |  | 100% | 2026-08-04 | 2026-08-06 | bar: T to T
Phase 02: Design (UML)
Gantt chart preparation | Neharika Wagle |  | 100% | 2026-08-06 | 2026-08-07 | bar: T to F
Use Case Diagram | Neharika Wagle |  | 100% | 2026-08-07 | 2026-08-08 | bar: F to S
Class Diagram | Neharika Wagle |  | 100% | 2026-08-08 | 2026-08-09 | bar: S to S
Sequence Diagram | Neharika Wagle |  | 100% | 2026-08-09 | 2026-08-10 | bar: S to M
Activity Diagram | Neharika Wagle |  | 100% | 2026-08-10 | 2026-08-11 | bar: M to T
Phase 03: Testing & QA
GitHub branch, pull request and review | All Members |  | 100% | 2026-08-11 | 2026-08-13 | bar: T to T
Unit test case preparation | Priyanka Singh |  | 100% | 2026-08-12 | 2026-08-13 | bar: W to T
Integration test case preparation | Priyanka Singh |  | 100% | 2026-08-13 | 2026-08-14 | bar: T to F
System test case preparation | Priyanka Singh |  | 100% | 2026-08-14 | 2026-08-15 | bar: F to S
User Acceptance Testing (UAT) | Priyanka Singh |  | 100% | 2026-08-15 | 2026-08-16 | bar: S to S
Phase 04: Finalization
Evidence collection and organization | All Members |  | 100% | 2026-08-02 | 2026-08-18 | bar: S to T
Final report preparation | All Members |  | 50% | 2026-08-17 | 2026-08-20 | bar: M to T
Final review and submission | All Members |  | 50% | 2026-08-20 | 2026-08-21 | bar: T to F